## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Automatically extracting information from SADs | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Student: Helena Ólafsdóttir (940329T165) | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned |  |  |  |  | Done |  |  |  |  | Optional
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Supervisor: Michel Chaudron |  | Project Start Date: |  | 2019-01-14
|  |  | Project End Date: |  | 2019-06-03
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 49 |  | mars | [27 empty] | apríl
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-03-04 to 2019-04-28
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s | m | þ | m | f | f | l | s
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Extracting information from SADS
1 | Find appropriate extraction tool | Low Risk | Helena | 100% | 2019-01-14 | 6
2 | Extract information with structure from all SADs | Low Risk | Helena | 90% | 2019-01-20 | 1
Creating ground truth
3 | Review literature on AK categories & AK classification | Low Risk | Helena | 20% | 2019-01-21 | 7
4 | Determine granularity | Med Risk | Helena | 100% | 2019-01-21 | 7
5 | Determine AK categories | Med Risk | Helena | 50% | 2019-01-21 | 14
6 | Annotate the SADs | Med Risk | Helena | 0% | 2019-01-28 | 21
Feature Extraction
7 | Review appropriate literature | Low Risk | Helena | 0% | 2019-02-18 | 12
8 | Investigate and implement various techniques | Low Risk | Helena | 0% | 2019-02-20 | 14
Train and evaluate a classifier
10 | Review appropriate literature | Low Risk | Helena | 0% | 2019-02-27 | 14
11 | Investigate and implement different classification algorithms + evaluation | Low Risk | Helena | 0% | 2019-02-27 | 14
12 | Investigate and implement different DL classification algorithms + evaluation | Optional | Helena | 0% | 2019-03-13 | 7
13 | Investigate and implement unsupervised clustering algorithms + evaluation and comparison | Optional | Helena | 0% | 2019-03-20 | 5
14 | Investigate the effects of adding stackoverflow posts to the training set | Optional | Helena | 0% | 2019-03-25 | 2
Build a system for handling user queries
15 | Initial investigation of types of user queries | Med Risk | Helena | 0% | 2019-01-28 | 2
16 | Investigate types of user queries | Med Risk | Helena | 0% | 2019-03-27 | 7
17 | Investigate how classification can improve responses to user queries | Med Risk | Helena | 0% | 2019-03-27 | 14
18 | Investigate how to present results to the user | Med Risk | Helena | 0% | 2019-04-10 | 7
19 | Implement a system for handling user queries and responses | Low Risk | Helena | 0% | 2019-04-17 | 14
20 | Evaluate system using test users and make resulting adjustments | Med Risk | Helena | 0% | 2019-05-01 | 7
Thesis report and related work
21 | Write thesis report | Low Risk | Helena | 0% | 2019-02-20 | 89
22 | Submit Planning Report | Low Risk | Helena | 0% | 2019-02-01 | 1
23 | Submit Halftime Report | Low Risk | Helena | 0% | 2019-03-25 | 1
24 | Hand in first draft of Final Report | Goal | Helena | 0% | 2019-05-13 | 1
25 | Finish the final draft of the Final Report | Goal | Helena | 0% | 2019-05-20 | 1
26 | Attend 2 presentations | Low Risk | Helena | 0% | 2019-05-21 | 1
27 | Attend 1 presentation as opponent | Low Risk | Helena | 0% | 2019-05-22 | 1
28 | Presentation | Low Risk | Helena | 0% | 2019-05-27 | 1
29 | Submit final report | Low Risk | Helena | 0% | 2019-06-03 | 1
| Seminars | Low Risk | Helena
30 | Writing seminar II + preparation | Low Risk | Helena |  |  | 2

## Time log
Date | Tasks
2019-01-14 | Reviewing pdf extraction tools
2019-01-15 | Reviewing pdf extraction tools
2019-01-16 | Reviewing pdf extraction tools
2019-01-17 | Reviewing pdf extraction tools + reviewing data
2019-01-18 | Reviewing pdf extraction tools + reviewing data
2019-01-19 | Manual Extraction
2019-01-20 | Manual Extraction
2019-01-21 | Meeting with Michel, Sorting SADs and documents to create a final dataset
2019-01-22 | Manual Extraction
2019-01-23 | Manual Extraction
2019-01-24 | Manual Extraction
2019-01-25
2019-01-26
2019-01-27
2019-01-28 | Reviewing literature on software architecture categories
2019-01-29 | Reviewing literature on software architecture categories, annotating data
2019-01-30 | Annotating data, working on python code for data
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-18
2019-03-19
2019-03-20
2019-03-21
2019-03-22
2019-03-23
2019-03-24
2019-03-25
2019-03-26
2019-03-27
2019-03-28
2019-03-29
2019-03-30
2019-03-31
2019-04-01
2019-04-02
2019-04-03
2019-04-04
2019-04-05
2019-04-06
2019-04-07
2019-04-08
2019-04-09
2019-04-10
2019-04-11
2019-04-12
2019-04-13
2019-04-14
2019-04-15
2019-04-16
2019-04-17
2019-04-18
2019-04-19
2019-04-20
2019-04-21
2019-04-22
2019-04-23
2019-04-24
2019-04-25
2019-04-26
2019-04-27
2019-04-28
2019-04-29
2019-04-30
2019-05-01
2019-05-02
2019-05-03
2019-05-04
2019-05-05
2019-05-06
2019-05-07
2019-05-08
2019-05-09
2019-05-10
2019-05-11
2019-05-12
2019-05-13
2019-05-14
2019-05-15
2019-05-16
2019-05-17
2019-05-18
2019-05-19
2019-05-20
2019-05-21
2019-05-22
2019-05-23
2019-05-24
2019-05-25
2019-05-26
2019-05-27
2019-05-28
2019-05-29
2019-05-30
2019-05-31
2019-06-01
2019-06-02
2019-06-03
2019-06-04
2019-06-05
2019-06-06